## Project Planning Updated
S.No | Project Name | Project Owner | AMC Reference | Emirate | Renew date | No. of PPMs | Total PPM duration | Contract Duration in Month | Days in Duration per PPM | Stage | PPM Date | PPM # | Year | Month | duplicate_count_by_project | Coverage | Property type | Brand | AC types | Indoors Qty | VRF OD Qty | DX Outdoor Qty | AHU Qty | AMC duration months | Total asset Qty
1 | Expo Idama Connect Center Conference 01/06/2024 | Sobin Sunny | AMC11157 | Dubai | 7/31/2026 | 4 | 40 | 3 | 10 | 2nd PPM done | 2025-10-24 | 1 | 2025 | Oct | 4 | PPM;Labor |  | Samsung | VRF;AHU;RAC;DX | 35 | 24 | 0 | 7 | 12 | 66
2 | Belgravia 3 - 01/01/2024) | Sobin Sunny | AMC11162 | Dubai | 7/31/2026 | 4 | 40 | 9 | 4.5 | 2nd PPM done | 2026-01-26 | 2 | 2026 | Jan | 4 | PPM;Labor | Education | Samsung | VRF;AHU;RAC;DX | 49 | 29 | 0 | 5 | 36 | 83
3 | Luma 21 - 01/01/2024) | Sobin Sunny | AMC11135 | Dubai | 7/31/2026 | 4 | 40 | 9 | 6 | 2nd PPM done | 2026-04-14 | 3 | 2026 | Apr | 4 | PPM;Labor | Education | Samsung | VRF;AHU;RAC;DX | 60 | 20 | 0 | 2 | 36 | 82
4 | Blue Bay - Full circle Labour Camp - 15/05/2024) | Siva V | AMC11136 | Dubai | 7/31/2026 | 4 | 40 | 9 | 29 | 2nd PPM done | 2026-07-14 | 4 | 2026 | Jul | 4 | PPM;Labor | Education | Samsung | VRF;AHU;RAC;DX | 487 | 93 | 0 | 4 | 36 | 584
5 | Jumeirah Bay LV 08 -19 Jan 2027 | Siva V | AMC11515 | Dubai | 7/31/2025 | 3 | 65 | 4 | 3 | Completed | 2024-07-11 | 1 | 2024 | Jul | 3 | PPM;Labor;Parts | Residential building | Samsung | VRF;AHU | 32 | 0 | 0 | 0 | 12 | 32
6 | Masdar City - 01/02/2025 | JALIL AHAMED | AMC11329 | Abu Dhabi | 7/31/2025 | 3 | 65 | 12 | 8 | Completed | 2024-11-15 | 2 | 2024 | Nov | 3 | PPM;Labor;Parts | Residential building | Samsung | VRF;AHU | 336 | 78 | 24 | 15 | 36 | 453
7 | Jotun accomodation al quoz - 01/04/2024 | Sobin Sunny | AMC11314 | Dubai | 7/31/2025 | 3 | 65 | 4 | 1 | Completed | 2025-03-04 | 3 | 2025 | Mar | 3 | PPM;Labor;Parts | Residential building | Samsung | VRF;AHU | 0 | 22 | 2 | 2 | 12 | 26
8 | Ace Base - Additional units - SBL,I-CAD-01/04/2025 | JALIL AHAMED | AMC11344 | Abu Dhabi | 06/01/2027 | 4 | 40 | 0.25 | 1 | 3rd PPM done | 2025-06-24 | 1 | 2025 | Jun | 4 | PPM;Labor | Government | Samsung | VRF | 10 | 6 | 0 | 0 | 1 | 16
9 | Al sultan building, Al qusais - 01/08/2025 | Sobin Sunny | AMC11338 | Dubai | 06/01/2027 | 4 | 40 | 3 | 21 | 3rd PPM done | 2025-09-29 | 2 | 2025 | Sep | 4 | PPM;Labor | Government | Samsung | VRF | 180 | 0 | 184 | 2 | 12 | 366
10 | Gardenia Living By Safe- Arjan - 01/06/2025 | Sobin Sunny | AMC11383 | Dubai | 06/01/2027 | 4 | 40 | 3 | 15 | 3rd PPM done | 2026-01-03 | 3 | 2026 | Jan | 4 | PPM;Labor | Government | Samsung | VRF | 259 | 52 | 0 | 3 | 12 | 314
11 | Baker Hughes SPC Facility - 01/06/2025 | JALIL AHAMED | AMC11352 | Abu Dhabi | 06/01/2027 | 4 | 40 | 3 | 1 | 3rd PPM done | 2026-03-24 | 4 | 2026 | Mar | 4 | PPM;Labor | Government | Samsung | VRF | 21 | 4 | 0 | 1 | 12 | 26
12 | White teak Company al barsha- 14/07/2025 | Sobin Sunny | AMC11373 | Dubai | 12/31/2026 | 4 | 18 | 3 | 2 | Welcome Email/WhatsApp sent | 2026-03-09 | 1 | 2026 | Mar | 4 | PPM;Labor | Residential building | Samsung | VRF | 18 | 1 | 18 | 1 | 12 | 38
13 | PGM Initiatives Warehouse - 23/07/2025 | Sobin Sunny | AMC11386 | Dubai | 12/31/2026 | 4 | 18 | 3 | 2 | Welcome Email/WhatsApp sent | 2026-06-10 | 2 | 2026 | Jun | 4 | PPM;Labor | Residential building | Samsung | VRF | 12 | 0 | 12 | 0 | 12 | 24
14 | Hala Equipment Trading LLC, DIC - 01/08/2025 | Sobin Sunny | AMC11390 | Dubai | 12/31/2026 | 4 | 18 | 3 | 2 | Welcome Email/WhatsApp sent | 2026-09-09 | 3 | 2026 | Sep | 4 | PPM;Labor | Residential building | Samsung | VRF | 40 | 6 | 0 | 2 | 12 | 48
15 | 2XL Showroom Al barsha - 29/07/2024 | Sobin Sunny | AMC11394 | Dubai | 12/31/2026 | 4 | 18 | 3 | 5 | Welcome Email/WhatsApp sent | 2026-12-09 | 4 | 2026 | Dec | 4 | PPM;Labor | Residential building | Samsung | VRF | 45 | 22 | 5 | 1 | 12 | 73
16 | Al Ain - FSFM Ladies Accommodation - 03/08/2025 | JALIL AHAMED | AMC11396 | Al-Ain | 3/31/2025 | 3 | 62 | 4 | 1 | Cancelled | 2024-05-15 | 1 | 2024 | May | 3 | PPM;Labor | Labor camp | Samsung | VRF | 0 | 2 | 0 | 2 | 12 | 4
17 | NBTC Head Office - Abudhabi - 05/09/2025 | JALIL AHAMED | AMC11435 | Abu Dhabi | 3/31/2025 | 3 | 62 | 4 | 3 | Cancelled | 2024-09-13 | 2 | 2024 | Sep | 3 | PPM;Labor | Labor camp | Samsung | VRF | 31 | 12 | 0 | 1 | 12 | 44
18 | DAEP - 01/10/2025 | Sobin Sunny | AMC11475 | Dubai | 3/31/2025 | 3 | 62 | 3 | 15 | Cancelled | 2025-01-26 | 3 | 2025 | Jan | 3 | PPM;Labor | Labor camp | Samsung | VRF | 461 | 83 | 60 | 10 | 9 | 614
19 | Blu Chocolate Sharjah - 01/11/2025 | Sobin Sunny | AMC11470 | Sharjah | 5/26/2026 | 4 | 24 | 3 | 2 | 3rd PPM done | 2025-08-25 | 1 | 2025 | Aug | 4 | PPM;Labor | Residential building | Unknown | VRF | 33 | 8 | 4 | 0 | 12 | 45
20 | Aroma camp C2 - 07/11/2025 | Sobin Sunny | AMC11474 | Dubai | 5/26/2026 | 4 | 24 | 3 | 10 | 3rd PPM done | 2025-10-27 | 2 | 2025 | Oct | 4 | PPM;Labor | Residential building | Unknown | VRF | 260 | 18 | 18 | 2 | 12 | 298
21 | SLB ACE Base Icad - 15/10/2025 | JALIL AHAMED | AMC11484 | Abu Dhabi | 5/26/2026 | 4 | 24 | 3 | 6 | 3rd PPM done | 2026-01-20 | 3 | 2026 | Jan | 4 | PPM;Labor | Residential building | Unknown | VRF | 165 | 36 | 7 | 12 | 12 | 220
22 | Al Ain Zapia Nature reserve Building & Food and Beverages Building - 01/11/2025 | JALIL AHAMED | AMC11491 | Al-Ain | 5/26/2026 | 4 | 24 | 3 | 4 | 3rd PPM done | 2026-04-20 | 4 | 2026 | Apr | 4 | PPM;Labor | Residential building | Unknown | VRF | 11 | 20 | 4 | 11 | 12 | 46
23 | Miza Warehouse - Zayed Port - 01/12/2025 | JALIL AHAMED | AMC11495 | Abu Dhabi | 12/31/2027 | 3 | 10 | 4 | 17 | Cancelled | 2025-04-15 | 1 | 2025 | Apr | 3 | PPM;Labor | Residential building | LG |  | 261 | 105 | 0 | 1 | 12 | 367
24 | FSFM Properties - 01/01/2026 | JALIL AHAMED | AMC11505 | Abu Dhabi | 12/31/2027 | 3 | 10 | 4 | 33 | Cancelled | 2025-08-15 | 2 | 2025 | Aug | 3 | PPM;Labor | Residential building | LG |  | 295 | 105 | 0 | 15 | 12 | 415
25 | Butterfly Building - 01/01/2026 | Sobin Sunny | AMC11513 | Dubai | 12/31/2027 | 3 | 10 | 0.33333 | 18 | Cancelled | 2025-12-08 | 3 | 2025 | Dec | 3 | PPM;Labor | Residential building | LG |  | 244 | 91 | 0 | 9 | 1 | 344
26 | Beach palace - 01/01/2026 | JALIL AHAMED | AMC11514 | Abu Dhabi | 12/31/2026 | 4 | 24 | 6 | 12 | Welcome Email/WhatsApp sent | 2026-03-05 | 1 | 2026 | Mar | 4 | PPM;Labor | Residential building | Samsung | VRF;AHU | 35 | 66 | 0 | 21 | 24 | 122
27 | Expo city Dubai Pavilions - 01/01/2026 | Sobin Sunny | AMC11506 | Dubai | 12/31/2026 | 4 | 24 | 3 | 24 | Welcome Email/WhatsApp sent | 2026-06-04 | 2 | 2026 | Jun | 4 | PPM;Labor | Residential building | Samsung | VRF;AHU | 109 | 441 | 0 | 0 | 12 | 550
28 | SFL Canusa AUH- 01/01/2026 | JALIL AHAMED | AMC11533 | Abu Dhabi | 12/31/2026 | 4 | 24 | 3 | 4 | Welcome Email/WhatsApp sent | 2026-09-04 | 3 | 2026 | Sep | 4 | PPM;Labor | Residential building | Samsung | VRF;AHU | 8 | 8 | 0 | 0 | 12 | 16
29 | 1244154 Highland Villa. - 01/01/2026 | JALIL AHAMED | AMC11537 | Abu Dhabi | 12/31/2026 | 4 | 24 | 3 | 1 | Welcome Email/WhatsApp sent | 2026-12-05 | 4 | 2026 | Dec | 4 | PPM;Labor | Residential building | Samsung | VRF;AHU | 4 | 2 | 0 | 1 | 12 | 7
30 | West field Nursery - 25/07/2025 | Sobin Sunny | AMC11440 | Dubai | 3/31/2025 | 2 | 2 | 6 | 2 | 1st PPM ongoing | 2025-01-17 | 1 | 2025 | Jan | 2 | PPM;Labor | Government |  |  | 32 | 9 | 0 | 1 | 12 | 42
31 | Yas Acres Golf Club & Country Club - Sole Proprietorship LLC - 01/04/2025 | JALIL AHAMED | AMC11303 | Abu Dhabi | 3/31/2025 | 2 | 2 | 6 | 9 | 1st PPM ongoing |  | 2 | 1900 | Jan | 2 | PPM;Labor | Government |  |  | 76 | 26 | 17 | 12 | 12 | 131
32 | Mr. Mohammed Benomar Murooj TH323- 01/07/2025 | Siva V | AMC11360 | Dubai | 5/14/2027 | 4 | 116 | 3 | 0.05 | 3rd PPM done | 2025-06-27 | 1 | 2025 | Jun | 4 | PPM;Labor;Parts | Labor camp | Samsung | VRF | 5 | 1 | 1 | 1 | 12 | 8
33 | Mr. Ali Zahid Murooj Th272- 29/08/2025 | Siva V | AMC11415 | Dubai | 5/14/2027 | 4 | 116 | 3 | 0.05 | 3rd PPM done | 2025-09-27 | 2 | 2025 | Sep | 4 | PPM;Labor;Parts | Labor camp | Samsung | VRF | 5 | 1 | 1 | 1 | 12 | 8
34 | Mr. Mesut Takseen Villa Sidra 2 V62- 12/02/2026 | Siva V | AMC11522 | Dubai | 5/14/2027 | 4 | 116 | 3 | 0.05 | 3rd PPM done | 2025-12-27 | 3 | 2025 | Dec | 4 | PPM;Labor;Parts | Labor camp | Samsung | VRF | 4 | 0 | 4 | 0 | 12 | 8
35 | Mr. Toufiqh Khan Murooj V548- 01/07/2025 | Siva V | AMC11362 | Dubai | 5/14/2027 | 4 | 116 | 3 | 0.05 | 3rd PPM done | 2026-03-27 | 4 | 2026 | Mar | 4 | PPM;Labor;Parts | Labor camp | Samsung | VRF | 8 | 1 | 1 | 1 | 12 | 11
36 | Mr. Kareem Rabieh Villa 100 Parkside 3- 28/06/2025 | Siva V | AMC11359 | Dubai | 4/13/2026 | 4 | 12 | 3 | 0.05 | Completed | 2024-05-30 | 1 | 2024 | May | 4 | PPM;Labor;Parts | Single villa | Samsung | VRF;AHU | 4 | 0 | 4 | 0 | 12 | 8
37 | DEEPA KHANNA MUROOJ TH466 | Siva V | AMC11385 | Dubai | 4/13/2026 | 4 | 12 | 3 | 0.05 | Completed | 2024-08-19 | 2 | 2024 | Aug | 4 | PPM;Labor;Parts | Single villa | Samsung | VRF;AHU | 5 | 1 | 1 | 1 | 12 | 8
38 | ***Mr. Gautam Singh Rathore Murooj V619- 05/11/2025 | Siva V | AMC11467 | Dubai | 4/13/2026 | 4 | 12 | 3 | 0.05 | Completed | 2024-11-25 | 3 | 2024 | Nov | 4 | PPM;Labor;Parts | Single villa | Samsung | VRF;AHU | 8 | 1 | 0 | 1 | 12 | 10
39 | Mr. Juha Samuli Murooj V165- 08/07/2025 | Siva V | AMC11367 | Dubai | 4/13/2026 | 4 | 12 | 3 | 0.05 | Completed | 2025-03-27 | 4 | 2025 | Mar | 4 | PPM;Labor;Parts | Single villa | Samsung | VRF;AHU | 8 | 1 | 1 | 1 | 12 | 11
40 | Mr. Hassan Belgravia BG 01 - 01/07/2025 | Siva V | AMC11363 | Dubai | 12/31/2027 | 3 | 45 | 4 | 0.05 | Welcome Email/WhatsApp sent | 2026-04-10 | 1 | 2026 | Apr | 3 | PPM;Labor | Commercial building | O'General | VRF | 5 | 1 | 0 | 0 | 12 | 6
41 | Mr. Joren Huijten Camelia 1 Villa 199- 09/07/2025 | Siva V | AMC11370 | Dubai | 12/31/2027 | 3 | 45 | 4 | 0.05 | Welcome Email/WhatsApp sent | 2026-08-12 | 2 | 2026 | Aug | 3 | PPM;Labor | Commercial building | O'General | VRF | 4 | 0 | 4 | 0 | 12 | 8
42 | Mr. Ali Matar Sidra1 V31- 12/11/2025 | Siva V | AMC11455 | Dubai | 12/31/2027 | 3 | 45 | 4 | 0.05 | Welcome Email/WhatsApp sent | 2026-12-10 | 3 | 2026 | Dec | 3 | PPM;Labor | Commercial building | O'General | VRF | 7 | 0 | 7 | 0 | 12 | 14
43 | Mr. John Alexander DSO D36- 30/01/2026 | Siva V | AMC11519 | Dubai | 3/31/2026 | 3 | 24 | 4 | 0.05 | Completed | 2025-06-01 | 1 | 2025 | Jun | 3 | PPM;Labor | Healthcare | Samsung | VRF | 10 | 2 | 1 | 0 | 12 | 13
44 | Praveen Narayan Nair-Murooj Al Furjan-Villa-584- 13/11/2025 | Siva V | AMC11478 | Dubai | 3/31/2026 | 3 | 24 | 4 | 0.05 | Completed | 2025-09-17 | 2 | 2025 | Sep | 3 | PPM;Labor | Healthcare | Samsung | VRF | 9 | 1 | 1 | 1 | 12 | 12
45 | Luma 22 3 Bed - 125 (East Block) - 01/11/2025 | Siva V | AMC11464 | Dubai | 3/31/2026 | 3 | 24 | 4 | 0.05 | Completed | 2026-01-23 | 3 | 2026 | Jan | 3 | PPM;Labor | Healthcare | Samsung | VRF | 4 | 1 | 1 | 0 | 12 | 6
46 | ***Ms. Daneyeh Shafei Murooj V212- 13/11/2025 | Siva V | AMC11479 | Dubai | 09/02/2025 | 3 | 3 | 4 | 0.05 | Completed | 2024-09-05 | 1 | 2024 | Sep | 3 | PPM;Labor;Parts | Single villa | Samsung | VRF | 8 | 1 | 1 | 1 | 12 | 11
47 | Al Waheda Villa - Tariq- 11/11/2025 | Siva V | AMC11500 | Dubai | 09/02/2025 | 3 | 3 | 4 | 0.05 | Completed | 2025-02-25 | 2 | 2025 | Feb | 3 | PPM;Labor;Parts | Single villa | Samsung | VRF | 17 | 4 | 0 | 0 | 12 | 21
48 | Mr-Khalil-Sidra 2 Villa 298- 02/10/2025 | Siva V | AMC11452 | Dubai | 09/02/2025 | 3 | 3 | 4 | 0.05 | Completed | 2025-05-06 | 3 | 2025 | May | 3 | PPM;Labor;Parts | Single villa | Samsung | VRF | 6 | 0 | 6 | 0 | 12 | 12
49 | ***Ms. Gagandeep & Mr. Ashish AR3 Joy V523- 15/11/2025 | Siva V | AMC11471 | Dubai | 9/30/2027 | 4 | 7 | 3 | 0.05 | 1st PPM done | 2025-12-05 | 1 | 2025 | Dec | 4 | PPM;Labor;Computer insp. | Retails & shops | LG | VRF | 4 | 0 | 4 | 0 | 12 | 8
50 | Mr. Imran Sayyed Murooj V595- 21/07/2025 | Siva V | AMC11382 | Dubai | 9/30/2027 | 4 | 7 | 3 | 0.05 | 1st PPM done | 2026-03-20 | 2 | 2026 | Mar | 4 | PPM;Labor;Computer insp. | Retails & shops | LG | VRF | 9 | 1 | 1 | 1 | 12 | 12
51 | Dr. Abo Bakr al Khair Astoria JVC A2- 22/07/2025 | Siva V | AMC11379 | Dubai | 9/30/2027 | 4 | 7 | 3 | 0.05 | 1st PPM done | 2026-06-11 | 3 | 2026 | Jun | 4 | PPM;Labor;Computer insp. | Retails & shops | LG | VRF | 7 | 1 | 0 | 0 | 12 | 8
52 | Antoine-Fairway-Villa-18- 01/09/2025 | Siva V | AMC11417 | Dubai | 9/30/2027 | 4 | 7 | 3 | 0.05 | 1st PPM done | 2026-09-19 | 4 | 2026 | Sep | 4 | PPM;Labor;Computer insp. | Retails & shops | LG | VRF | 15 | 4 | 1 | 2 | 12 | 22
53 | Mr. Hemant Kesana Luma 22 F216- 17/11/2025 | Siva V | AMC11480 | Dubai | 9/30/2027 | 3 | 28 | 4 | 0.05 | 1st PPM done | 2026-01-13 | 1 | 2026 | Jan | 3 | PPM;Labor;Computer insp. | Commercial building | Samsung | VRF;DX;AHU | 3 | 1 | 0 | 0 | 12 | 4
54 | Mr. Marcin Arabian Ranches 2, Camelia 2, Villa 21- 10/09/2025 | Siva V | AMC11406 | Dubai | 9/30/2027 | 3 | 28 | 4 | 0.05 | 1st PPM done | 2026-04-20 | 2 | 2026 | Apr | 3 | PPM;Labor;Computer insp. | Commercial building | Samsung | VRF;DX;AHU | 4 | 0 | 4 | 0 | 12 | 8
55 | Mr. Wissam Elassaad Murooj V507- 22/07/2025 | Siva V | AMC11380 | Dubai | 9/30/2027 | 3 | 28 | 4 | 0.05 | 1st PPM done | 2026-07-20 | 3 | 2026 | Jul | 3 | PPM;Labor;Computer insp. | Commercial building | Samsung | VRF;DX;AHU | 8 | 1 | 1 | 1 | 12 | 11
56 | Mr. Mustafa Alizzi Murooj V248- 24/11/2025 | Siva V | AMC11486 | Dubai | 1/17/2026 | 3 | 30 | 4 | 0.05 | Completed | 2025-02-04 | 1 | 2025 | Feb | 3 | PPM;Labor | Residential building | O'General | VRF | 9 | 1 | 1 | 1 | 12 | 12
57 | ***Mr. Mazen El Moghazy Club V23- 25/11/2025 | Siva V | AMC11488 | Dubai | 1/17/2026 | 3 | 30 | 4 | 0.05 | Completed | 2025-05-19 | 2 | 2025 | May | 3 | PPM;Labor | Residential building | O'General | VRF | 5 | 0 | 5 | 0 | 12 | 10
58 | faisal shora sidra 2 V184 | Siva V | AMC11476 | Dubai | 1/17/2026 | 3 | 30 | 4 | 0.05 | Completed | 2025-09-05 | 3 | 2025 | Sep | 3 | PPM;Labor | Residential building | O'General | VRF | 4 | 0 | 4 | 0 | 12 | 8
59 | Mr. Mohammad Al Olama Nad Al Sheba V20- 04/07/2025 | Siva V | AMC11364 | Dubai | 1/31/2026 | 2 | 20 | 6 | 0.05 | 2nd PPM done | 2025-04-23 | 1 | 2025 | Apr | 2 | PPM;Labor | Commercial building |  | VRF | 11 | 4 | 5 | 0 | 12 | 20
60 | ***Ms. SoJeong AR3 Spring V20- 21/11/2025 | Siva V | AMC11483 | Dubai | 1/31/2026 | 2 | 20 | 6 | 0.05 | 2nd PPM done | 2026-01-19 | 2 | 2026 | Jan | 2 | PPM;Labor | Commercial building |  | VRF | 4 | 0 | 4 | 0 | 12 | 8
61 | Mr. George Makhoul Villa- 17/04/2025 | Siva V | AMC11316 | Dubai | 01/09/2026 | 3 | 2 | 4 | 0.05 | PPMs completed | 2025-01-13 | 1 | 2025 | Jan | 3 | PPM;Labor;Parts | Single villa | Samsung |  | 42 | 13 | 0 | 1 | 12 | 56
62 | Mr. Lalit Motwani Murooj TH277- 29/07/2025 | Siva V | AMC11381 | Dubai | 01/09/2026 | 3 | 2 | 4 | 0.05 | PPMs completed | 2025-05-20 | 2 | 2025 | May | 3 | PPM;Labor;Parts | Single villa | Samsung |  | 5 | 1 | 1 | 1 | 12 | 8
63 | ***Mrs. Sabina Shelton AR3 Joy V774- 24/07/2025 | Siva V | AMC11384 | Dubai | 01/09/2026 | 3 | 2 | 4 | 0.05 | PPMs completed | 2025-09-20 | 3 | 2025 | Sep | 3 | PPM;Labor;Parts | Single villa | Samsung |  | 4 | 0 | 4 | 0 | 12 | 8
64 | ***Mr. Malek Karali Murooj V513- 12/11/2025 | Siva V | AMC11477 | Dubai | 1/16/2026 | 3 | 2 | 4 | 0.05 | PPMs completed | 2025-01-17 | 1 | 2025 | Jan | 3 | PPM;Labor;Parts | Single villa | Samsung | VRF;AHU;RAC | 8 | 1 | 1 | 1 | 12 | 11
65 | Avtar Mamotra-Arabian Ranches-3-Villa-592- 01/07/2025 | Siva V | AMC11365 | Dubai | 1/16/2026 | 3 | 2 | 4 | 0.05 | PPMs completed | 2025-05-08 | 2 | 2025 | May | 3 | PPM;Labor;Parts | Single villa | Samsung | VRF;AHU;RAC | 4 | 0 | 4 | 0 | 12 | 8
66 | Ms. Mariam Shahid AR3 Joy 531- 29/09/2025 | Siva V | AMC11437 | Dubai | 1/16/2026 | 3 | 2 | 4 | 0.05 | PPMs completed | 2025-08-05 | 3 | 2025 | Aug | 3 | PPM;Labor;Parts | Single villa | Samsung | VRF;AHU;RAC | 4 | 0 | 4 | 0 | 12 | 8
67 | Mr. Sergey Vasilyev Luma 22 F240- 28/11/2025 | Siva V | AMC11490 | Dubai | 1/19/2026 | 3 | 9 | 4 | 0.05 | Completed | 2025-03-17 | 1 | 2025 | Mar | 3 | PPM;Labor;Parts | Single villa | Samsung |  | 2 | 1 | 0 | 0 | 12 | 3
68 | ***Mr. Mohammad El- Lakkis Mag V18 Furjan- 28/07/2025 | Siva V | AMC11387 | Dubai | 1/19/2026 | 3 | 9 | 4 | 0.05 | Completed | 2025-06-06 | 2 | 2025 | Jun | 3 | PPM;Labor;Parts | Single villa | Samsung |  | 9 | 0 | 9 | 0 | 12 | 18
69 | ***Ms. Namrata Kaul Murooj TH332- 31/07/2025 | Siva V | AMC11389 | Dubai | 1/19/2026 | 3 | 9 | 4 | 0.05 | Completed | 2025-11-06 | 3 | 2025 | Nov | 3 | PPM;Labor;Parts | Single villa | Samsung |  | 4 | 1 | 1 | 1 | 12 | 7
70 | EMIRATES HILLS VILLA R40 | Siva V | AMC11469 | Dubai | 1/29/2026 | 3 | 3 | 4 | 0.05 | 2nd PPM done | 2025-02-07 | 1 | 2025 | Feb | 3 | PPM;Labor | Single villa | Samsung | VRF | 22 | 3 | 4 | 0 | 12 | 29
71 | JOHN BRITTON TH107 | Siva V | AMC11349 | Dubai | 1/29/2026 | 3 | 3 | 4 | 0.05 | 2nd PPM done | 2025-08-01 | 2 | 2025 | Aug | 3 | PPM;Labor | Single villa | Samsung | VRF | 5 | 1 | 1 | 1 | 12 | 8
72 | Lifco Sharjah -10/07/2025 | Sobin Sunny | AMC11378 | Sharjah | 2026-09-07 | 2 | 24 | 12 | 12 | 1st PPM done | 2026-03-01 | 2 | 2026 | Mar | 2 | PPM;Labor;Parts | Commercial building | Samsung | DX | 151 | 0 | 151 | 0 | 12 | 314

## Team
Technician Name | City | Driver | Skill Level | New Level | Category | Annual leave | Project Owner | Remark
Abhimanue | Abu Dhabi , Al-Ain | N | L2 | L2 | PPM |  | JALIL AHAMED
Afroz | Abu Dhabi , Al-Ain | Y | L0 | L1 | PPM |  | JALIL AHAMED
Ansari | Dubai, Sharjah | N | L2 | L2 | PPM |  | Sobin Sunny
Daryl | Dubai, Sharjah | N | L2 | L2 | PPM |  | Sobin Sunny
Hussnain | Dubai, Sharjah | N | L1 | L1 | PPM |  | Sobin Sunny
Imran | Dubai, Sharjah | Y | L0 | L0 | PPM |  | Sobin Sunny
Irfan | Dubai, Sharjah | Y | L1 | L1 | PPM |  | Sobin Sunny
Ismail | RAK | N | L2 | L2 | PPM | 46082 | JALIL AHAMED
Mahtab | Abu Dhabi , Al-Ain | N | L2 | L3 | PPM |  | JALIL AHAMED
Moosa | Abu Dhabi , Al-Ain | Y | L2 | L2 | PPM |  | JALIL AHAMED
Rajeeb | Dubai, Sharjah | N | L1 | L1 | PPM | 46083 | Sobin Sunny
SHAZAD | Dubai, Sharjah | Y | L2 | L2 | PPM |  | Sobin Sunny
Thanis | Dubai, Sharjah | Y | L3 | L3 | PPM |  | Siva V
Yadav | Dubai, Sharjah | N | L0 | L0 | PPM |  | Sobin Sunny
Zilani | RAK | Y | L3 | L4 | PPM |  | JALIL AHAMED
Jayaprasad | Dubai, Sharjah | N | L0 | L0 | PPM |  | Sobin Sunny | Backup
Sitaram | Dubai, Sharjah | N | L0 | L0 | PPM |  | Siva V | Backup
Ranjit Biswarma | Dubai, Sharjah | N | L0 | L0 | PPM |  | Sobin Sunny | Backup
jawgat | Dubai, Sharjah | N | L0 | L1 | PPM |  | Sobin Sunny | Backup

## users
phone | name | role
565069985 | jakir | admin
502768891 | Siva | admin
543384161 | Samer | admin
504220356 | Sobin | admin
562218946 | jalil | admin
564227780 | inamul | PPM
508802486 | Thanis | PPM
504227514 | Ravi Yadav | PPM
562218792 | Rajeeb Thakur | PPM
562217432 | Irfan | PPM
503371008 | Ansari | PPM
565265112 | Daryl | PPM
563799356 | Hussain | PPM
553285621 | Jawthat | PPM
568325418 | SHAZAD | PPM
504227695 | Mahtab | PPM
564740877 | waqas | PPM
‎566016939 | Asif | PPM
543378728 | Dhavooth | PPM
544923726 | Afroz | PPM
565621742 | Tokir | PPM
504221390 | Moosa | PPM
234567890 | Sitaram | PPM
345678901 | Samim | PPM
456789012 | abhimanue | PPM
503285621 | Jawthath | PPM
509288074 | Ranjit Biswakarma | PPM
789012345 | Yadav | PPM
890123456 | Zilani | PPM
123456789 | Jayaprasath | Helper
123456789 | Siraf | Helper
123456789 | Manjeet | Helper
123456789 | Ranjit | Helper
123456789 | Akbar | Helper
123456789 | Arjun | Helper
123456789 | Arvind | Helper
123456789 | Azzarudhin | Helper
123456789 | Danish | Helper
123456789 | Geayash | Helper
123456789 | habib | Helper
123456789 | Hazrat | Helper
123456789 | Imran | Helper
123456789 | Jawthath | Helper
123456789 | Jayaprasath | Helper
123456789 | Majit | Helper
123456789 | Musharaf | Helper
123456789 | Saddam | Helper
123456789 | Shah Faisal | Helper
123456789 | Shazib | Helper
123456789 | Sitaram | Helper
123456789 | Umer | Helper
123456789 | Waqas | Helper
123456789 | Sajid | Helper
123456789 | Asif | Helper
123456789 | Thovatoo | Helper

## Inputs
Date | Project Owner | AMC Reference | Project Name (Backend) | Emirate | PPM # | PPM Date | Indoors Completed | VRF OD Completed | DX Outdoor Completed | AHU Completed | Technician name 1 | Technician name 2 | Technician name 3 | Helper name 1 | Helper name 2 | Helper name 3 | Submitted By (Phone) | Submitted At
2026-02-25 | Sobin Sunny | AMC11109 | zayed educational complex-al Mizhar - 01/08/2024) | Dubai | 1 | 2025-10-24 00:00:00 | 3 | 2 | 2 | 2 | [6 empty] | 565069985 | 2026-02-25 13:44:13
2026-02-25 | Sobin Sunny | AMC11109 | zayed educational complex-al Mizhar - 01/08/2024) | Dubai | 1 | 2025-10-24 00:00:00 | 0 | 0 | 0 | 0 | Abhimanue |  |  | Afroz |  |  | 565069985 | 2026-02-25 13:44:25
2026-02-25 | Siva V | AMC11136 | Blue Bay - Full circle Labour Camp - 15/05/2024) | Dubai | 2 | 2025-09-27 00:00:00 | 2 | 2 | 0 | 4 | [6 empty] | 564227780 | 2026-02-25 13:46:02
2026-02-25 | Siva V | AMC11136 | Blue Bay - Full circle Labour Camp - 15/05/2024) | Dubai | 2 | 2025-09-27 00:00:00 | 0 | 0 | 0 | 0 | Daryl |  |  | Abhimanue |  |  | 564227780 | 2026-02-25 13:46:31
2026-02-25 | Siva V | AMC11334 | Mr. Edwin Haver Villa 210 Murooj- 19/05/2025 | Dubai | 3 | 2026-01-21 00:00:00 | 2 | 2 | 2 | 2 | Ansari |  |  | Sitaram |  |  | 564227780 | 2026-02-25 14:02:59